## Sheet1
Sr No | Requirenment | Task | Estimate(hrs) | Remarks
1 | Configuration For Local Sync | Fetch & Store User Details to decide local sync option to display or not | ??? | Need to know which API to use?
|  | Screen Design for New Local Sync Option | 2
|  | Screen Design for selecting external hard disk | 1
|  | Store the current Configuration for the user | 4
|  | Unit Testing | 4
2 | Change Backup Destination | Screens Design for confirmation when user changes external drive | 3
|  | Functionality for deleting current data when user select delete option | 8
|  | Functionality for coping current data to default BBBSync directory when user selects that option | 8
|  | Unit Testing | 8
3 | Restore | Screen Design for restore option | 2
|  | Screen Design for Restore from Local Backup | 8
|  | Fetch current size of backed up data of both Local & Cloud to display against restore option | ??? | Need to know which API to use?
|  | Functionality to restore seleted data to desired location | 8
|  | Unit Testing | 16
4 | Backup Monitor Service | Modify current monitor service to include local sync option | 4
|  | Unit Testing | 4
5 | Daily Notification Mail | Modify current notification mail to include the local sync status | 16
|  | Notification mail if backup fails due to harddisk space | 16
|  | Unit Testing | 4
6 | Document Versioning | Screen Design for Document Versioning feature | 2
|  | Document Versioning functionality based on configuration | 40
|  | Unit Testing | 16
7 | Utilities | Utility for Encrypt & Decrypt file using AES algorithm | 8
|  | Utility for monitoring disk space size | 4
|  | Utility for identify external drive | 4
|  | Utility for making backup folder hidden & visible based on the logging status | 8
8 | Backup | Functionality to take backup of the selected folder to the selected exernal hard drive in secured way | 8
|  | Send backup information to server when local sync completed | ??? | Need to know which what information to send & how?
|  | Unit Testing | 8
|  | Total | 214